## Slide 1
MDATA 600 CAPSTONE
Crushed-Stone Aggregates Demand
Progress check & final scope decisions
Professor 1:1 • Friday, September 18, 2026
Joseph Schnee
Source: final_project_outline.qmd and its September 15–16 commit history

## Slide 2
TWO-DAY PROGRESS
From outline to working analysis
The project advanced in two focused evening work sessions.
DAY 1
SEP 15
Established the capstone outline
Defined three research questions, documented the source landscape, and organized the report into data, EDA, modeling, and findings sections.
DAY 2
SEP 16
Converted prompts into executable R
Added dataset construction, missingness checks, a histogram, correlation matrix, four predictor plots, and five linear model fits.
+171
LINES ADDED ON SEP 16
49
LINES REPLACED/REMOVED
5
REGRESSION MODELS CODED
1
FILE IN SCOPE
MDATA 600 • Progress Check • 18 September 2026
2

## Slide 3
CURRENT SCOPE
What the outline is trying to answer
All three questions use state-year observations from 2015–2023.
01
EXPLANATION
Which construction, economic, capacity, and cost indicators best explain state-level crushed-stone production?
02
LAGGED HIGHWAY SIGNAL
To what extent do prior-year highway capital outlays predict state-level production?
03
PREDICTION ACCURACY
How accurately can construction GDP, highway outlays, and residential permits predict production?
Current framing: explanatory analysis; crushed-stone tons are used as a proxy for demand; future forecasting is not advised.
MDATA 600 • Progress Check • 18 September 2026
3

## Slide 4
STATUS AGAINST OBJECTIVES
The analysis backbone is now in place
Working code exists for the data, exploratory, and initial modeling stages.
450
STATE-YEAR ROWS
50
U.S. STATES
2015–23
ANALYSIS WINDOW
14
RQ1 FIELDS
427
OBSERVED TARGETS
DATA PREP
Builds residential permits, selects the RQ1 fields, checks duplicate state-year keys, and reports missingness.
Complete
EDA
Histogram and correlation matrix are coded; four predictor-versus-production plots are present but need labeling fixes.
In progress
MODELING
Four simple regressions plus one four-predictor multiple regression run; result tables and interpretation remain unwritten.
In progress
MDATA 600 • Progress Check • 18 September 2026
4

## Slide 5
PROVISIONAL SIGNAL
Initial regressions show strong pooled associations
These are in-sample results from the code currently in the outline—not final findings.
Private nonres. spending
R² 0.551
n=427
Residential permits
R² 0.559
n=427
Highway outlays
R² 0.682
n=427
Construction employment
R² 0.705
n=310
Four-predictor model
R² 0.756
n=310
What this suggests
Highway outlays have the strongest simple relationship among the fully observed predictors (r = 0.849).
The four-predictor model reaches R² = 0.756 in the available complete cases.
State scale, repeated observations, and differing sample sizes mean these are provisional associations—not forecasting evidence.
R² scale
0
.25
.50
.75
1.0
MDATA 600 • Progress Check • 18 September 2026
5

## Slide 6
EXECUTION ROADBLOCKS
Five issues to resolve before finalizing the analysis
The most important problem is a mismatch between the written missing-value rule and the code.
1
Missing-data rule
The text says 23 predictor rows were removed, but the code removes only the 23 missing target rows. Employment is missing in 126 rows, so Model 4 and Model 5 use only 310 observations.
2
Plot labels
Several plot titles and x-axis labels describe different variables than the code actually plots.
3
Portability
The input CSV is referenced with an absolute local path, so the document will not run on another machine without editing.
4
Results narrative
Interpretations under the summary table and histogram are still placeholders; coefficient and model-fit sections are not yet populated.
5
Scope-to-code alignment
The code currently analyzes RQ1. Prior-year highway prediction and formal predictive accuracy are stated as RQ2/RQ3 but are not implemented.
MDATA 600 • Progress Check • 18 September 2026
6

## Slide 7
SCOPE DECISION FOR FRIDAY
Recommendation: lock one explanatory question
This aligns the final scope with the code that is already furthest along and can be completed defensibly.
Recommended final question
Which selected construction and economic indicators are most strongly associated with state-level crushed-stone production from 2015–2023?
Keep
State-year design • 2015–2023 • Four predictors • Multiple linear regression • Association-only claims
Decisions requested
1
Approve consolidating the three questions into one explanatory question.
2
Confirm the four-predictor set and complete-case rule.
3
Confirm whether repeated-state structure needs a course-level adjustment or limitation only.
After approval: fix missingness + labels → complete model tables and diagnostics → write findings → render and proofread
MDATA 600 • Progress Check • 18 September 2026
7